## Sheet1
Task | Start Date | End Date | Duration
First Deliverable |  | 2017-11-23 | 43062
Ethics Form Completed |  | 2017-11-23 | 43062
Research Available Algorithms | 2017-10-01 | 2017-10-08 | 7 | I will update these dates following Tuesday's Meeting
Literature Review |  |  | 0
Requirements Analysis |  |  | 0
Risk Analysis |  |  | 0
0
Interview with Supervisor |  | 2017-12-15 | 43084
0
Final Deliverable |  | 2018-04-23 | 43213
Draft Deliverable |  | 2018-03-16 | 43175
0
Development of Package |  |  | 0
Initial Planning |  |  | 0
Implementation |  |  | 0
Unit Testing |  |  | 0
Package Documentation |  |  | 0
0
Write Dissertation Draft |  |  | 0
Improve from Feedback |  |  | 0
Write Dissertation Final |  |  | 0
0
Poster Deliverable |  | 2018-05-07 | 43227
Poster Design | 2018-04-20 | 2018-04-22 | 2
Create Poster | 2018-04-22 | 2018-04-25 | 3
Print Poster | 2018-04-25 | 2018-04-26 | 1
Prepare for Session | 2018-04-26 | 2018-05-03 | 7
Poster Session | 2018-05-04 | 2018-05-04 | 0
Poster Submitted | 2018-05-05 | 2018-05-07 | 2