## Sheet1
Task | Start Date | End Date | Duration
First Deliverable | 2017-10-01 | 2017-11-23 | 53
Ethics Form Completed | 2017-11-22 | 2017-11-23 | 1
Research Available Algorithms | 2017-10-01 | 2017-10-08 | 7 | I will update these dates following Tuesday's Meeting
Literature Review | 2017-10-08 | 2017-11-10 | 33 | This graph is also setup for data to be entered
Requirements Analysis | 2017-11-10 | 2017-11-14 | 4 | I must decide on good deadlines and good ordering of tasks
Risk Analysis | 2017-11-14 | 2017-11-16 | 2
Poster Deliverable | 2018-04-20 | 2018-05-07 | 17
Poster Design | 2018-04-20 | 2018-04-22 | 2
Create Poster | 2018-04-22 | 2018-04-25 | 3
Print Poster | 2018-04-25 | 2018-04-26 | 1
Prepare for Session | 2018-04-26 | 2018-05-03 | 7
Poster Session | 2018-05-04 | 2018-05-04 | 0
Poster Submitted | 2018-05-05 | 2018-05-07 | 2